## Sheet
کد فرآيند | نام مدرک | مهلت اولين ارائه | CONTRACT & LOCATION CODE | DOCUMENT CODE | CLASS | كامنت كارشناس | PHASE CODE | Client Letter No. | Comment | Comment Sheet No. | Consultant Letter No. | AREA CODE | EQUIPMENT CODE | EQUIPMENT INDENT | DISCIPLINE CODE | SERIAL CODE | .W.F | Client Man-hours | Transmittal No. | Trans Date | Client Reciept Date | Consultant Letter Date | Client Letter Date | وضعيت ارسالي | وضعيت دريافتي | سر ورژن مدرک داخلي | شمارنده ورژن مدرک داخلي | سر ورژن مدرک توليدي | شمارنده ورژن مدرک توليدي | سر ورژن مدرک ارسالي | شمارنده ورژن مدرک ارسالي | شاخص کار
50904-D-04-XXX-00-178-GN-0001 | Commissioning & Start Up And Operating Manual |  | 50904 | 178 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | GN | 0001 | 0.48 | [6 empty] | Not Issued | Not Issued
50904-D-04-XXX-00-186-PR-0004 | Process Block Diagram |  | 50904 | 186 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | PR | 0004 | 0.48 | [6 empty] | Not Issued | Not Issued
50904-D-04-XXX-00-186-PL-0120 | Pipeline Crossing Detail number 21 for YAZD-NAEEN |  | 50904 | 186 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | PL | 0120 | 0.45 | [6 empty] | Not Issued | Not Issued
50904-D-04-XXX-00-186-PL-0121 | Pipeline Crossing Detail number 22 for YAZD-NAEEN |  | 50904 | 186 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | PL | 0121 | 0.45 | [6 empty] | Not Issued | Not Issued
50904-D-04-XXX-00-186-PL-0122 | Pipeline Crossing Detail number 23 for YAZD-NAEEN |  | 50904 | 186 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | PL | 0122 | 0.45 | [6 empty] | Not Issued | Not Issued
50904-D-04-XXX-00-186-CP-0001 | Cathodic Protection System Installation Layout |  | 50904 | 186 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | CP | 0001 | 0.65 | [6 empty] | Not Issued | Not Issued
50904-D-04-XXX-00-158-CP-0001 | MTO for Cathodic Protection System |  | 50904 | 158 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | CP | 0001 | 0.48 | [6 empty] | Not Issued | Not Issued
55000-D-04-XXX-00-101-PL-0001 | Anchor Flange Specification |  | 55000 | 101 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | PL | 0001 | 0.08 | [6 empty] | Not Issued | Not Issued
55000-D-04-XXX-00-105-PL-0001 | Anchor Flange Data Sheet |  | 55000 | 105 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | PL | 0001 | 0.08 | [6 empty] | Not Issued | Not Issued
55000-D-04-XXX-00-186-PL-0208 | Pipeline Crossing Detail number 9 for Branch of YAZD |  | 55000 | 186 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | PL | 0208 | 0.24 | [6 empty] | Not Issued | Not Issued
55000-D-04-XXX-00-139-PL-0001 | Hydrostatic Test Diagram for Branch of YAZD |  | 55000 | 139 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | PL | 0001 | 0.48 | [6 empty] | Not Issued | Not Issued
50904-D-04-XXX-00-190-PL-0004 | TBE for Vent and Main ByDass Valves |  | 50904 | 190 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | PL | 0004 | 0.24 | [6 empty] | Not Issued | Not Issued
50904-D-04-XXX-00-190-CP-0001 | TBE for Transformer Rectifier |  | 50904 | 190 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | CP | 0001 | 0.24 | [6 empty] | Not Issued | Not Issued
50904-D-04-XXX-00-190-CP-0002 | TBE for Dermanent Cell |  | 50904 | 190 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | CP | 0002 | 0.24 | [6 empty] | Not Issued | Not Issued
50904-D-04-XXX-00-190-CP-0003 | TBE for High silicon Cast Iron |  | 50904 | 190 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | CP | 0003 | 0.24 | [6 empty] | Not Issued | Not Issued
50904-D-04-XXX-00-190-CP-0004 | TBE for AC Danel |  | 50904 | 190 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | CP | 0004 | 0.24 | [6 empty] | Not Issued | Not Issued
50904-D-04-XXX-00-190-CP-0005 | TBE for Zinc Earthing Cell |  | 50904 | 190 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | CP | 0005 | 0.24 | [6 empty] | Not Issued | Not Issued
55000-D-04-XXX-00-190-PI-0001 | TBE for Bulk material |  | 55000 | 190 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | PI | 0001 | 0.48 | [6 empty] | Not Issued | Not Issued
55000-D-04-XXX-00-172-PL-0001 | Material Requisition for Anchor Flange |  | 55000 | 172 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | PL | 0001 | 0.16 | [6 empty] | Not Issued | Not Issued
55000-D-04-XXX-00-190-PL-0001 | TBE for Anchor Flange |  | 55000 | 190 | 00 |  | D |  |  |  |  | 04 | XXX | 00 | PL | 0001 | 0.24 | [6 empty] | Not Issued | Not Issued